## Slide 1: Scope baseline
SUPPLIER DATA COLLECTION · PHASE 2
What we will build, how we will know each item is done, and what will be different for suppliers and analysts.
Automation Center of Excellence · [meeting date]
Scope gate · for approval
Notes: Phase 2 is already approved. This meeting ratifies what phase 2 means: the scope baseline. Say that in one sentence and move to the next slide, which lists exactly what is being decided.

## Slide 2: Phase 2 is approved. Today we fix what it contains, how each item is judged done, and what changes for the people who use SDC.
WHAT THIS GATE DECIDES
1 · Approve
The eleven scope elements as defined in the requirements register, baseline v1.0.
2 · Agree
The “done when” test for each element: the observable result that closes it.
3 · Acknowledge
The changes in how suppliers and analysts will work once each element is live.
Change control
After today, any change to this baseline goes through [change authority]. That includes changes I propose.
Not decided today: detailed design, dates finer than the stage plan in the appendix, and the definitions of the two elements still in discovery (slide 9).
2
Notes: Read the three decisions aloud, then the change-control line, then the "not decided today" line. Name the change authority by name and role. Saying "that includes changes I propose" out loud is deliberate: it tells the room the baseline is real and that you are bound by it too. Do not open the content yet.

## Slide 3: Eleven elements in four groups; three carry a question for this room, two are approved subject to definition.
SCOPE BASELINE V1.0
Supplier experience
R01 Master data upload · D1
R02 Rate calculator
R03 In‑flight changes · D2
R04 Flag for review
Analyst experience
R06 Configuration web app · D3
R08 Error review in context
R09 Batch add suppliers
R10 Seed‑data validation
Platform foundation
R05 Template modifications
carries the task‑model change that R03 and R11 build on
R07 Analyst training (rollout)
Subject to definition
R11 SOW support
R02 Rate rules (behind the calculator)
definitions return at the next gate
D1–D3 are decisions taken today (slide 10). Elements with no marker are proposed as written in the register; the in/out detail is in the appendix.
3
Notes: This is the baseline. Walk the four groups in ten seconds each. Point out the D markers: those three elements need an answer from this room before they are baselined. Everything else is proposed as written in the register. The next three slides are the detail, one group each.

## Slide 4: Suppliers get it right the first time, inside the portal.
GROUP 1 · SUPPLIER EXPERIENCE
Element | We will | Done when | What changes for you
R01 Master data upload | Add a secure upload step in the portal for client reference data, with analyst access. | An analyst finds a new implementation’s reference data in the portal; none arrives by email. | Reference data is uploaded, not emailed. Whether the system also uses it is decision D1.
R02 Rate calculator | Put a rate calculator in the supplier form, with supplier‑facing messages and an override. | A supplier sees the calculated rate before submitting; rate rounds per supplier fall below today’s [__]. | Submitted rates match the calculator or carry an override reason. The rules behind it are pending (slide 9).
R03 In‑flight changes | Add a supplier “request an edit” action, an attributed edit history, and an analyst notification. | A supplier requests an edit in the portal and the analyst sees who changed what, and when. | Edits after submission go through the portal; email edits are no longer worked. Which states allow it is decision D2.
R04 Flag for review | Add a submission‑level flag that creates an analyst task and bypasses the rework loop. | A flagged submission lands with the analyst as a task, without a rework cycle. | “Flag for review” replaces placeholder values entered to pass validation.
Not in this group: analyst review of calculated rates; analyst edits made on a supplier’s behalf; field‑level flags.
4
Notes: Each row in one breath, left to right: what we will do, the test that closes it, what the supplier will notice. The "done when" column is the one to get agreement on; if someone disputes a test, that is the useful conversation. The footnote is the out-of-scope items a stakeholder might be expecting; the full in/out list is in appendix A.

## Slide 5: Analysts configure and review without leaving the system.
GROUP 2 · ANALYST EXPERIENCE
Element | We will | Done when | What changes for you
R06 Configuration web app | Replace the chosen configuration steps with analyst web pages that apply the same checks the workbook does today. | An analyst completes the chosen configuration steps without opening the workbook. | Those steps move to a page; the workbook remains for the rest. Which steps go first is decision D3.
R08 Error review in context | Show validation failures in the shape the data was submitted. | An analyst reviews a failed submission without reformatting it. | Errors appear against the submitted rows, not in a separate list.
R09 Batch add suppliers | Add several suppliers to a started implementation in one action. | An analyst adds several suppliers to a live implementation in one action. | One batch action replaces per‑supplier setup after kickoff.
R10 Seed‑data validation | Validate seed data against the configuration at load and report mismatches to the analyst. | A seed or configuration mismatch reaches the analyst before any supplier sees it. | A validation report appears at load; a mismatched load stops until corrected.
Not in this group: changes to the validation rules themselves; removing or reassigning suppliers; automatic correction of seed data.
5
Notes: Same reading pattern as the previous slide. R06 is the large element here and carries decision D3. R08–R10 are small and independent; if anyone wants to trade scope, these are not where the leverage is.

## Slide 6: One change to the task model lets templates change mid‑implementation, and three requirements build on it.
GROUP 3 · PLATFORM FOUNDATION · R05 TEMPLATE MODIFICATIONS
Today: one task, one chain of states
Assigned
Submitted
Validated
Approved
A supplier holds one task that only moves forward. A template change or an edit after submission means stepping outside the system.
Phase 2: several tasks per supplier, each versioned
Template A · v2
submitted → edit requested → re‑approved
Template B · v1
assigned → in progress
Milestone doc · v1
not yet released
Versions and attribution are built in. Template updates, edits and SOW documents become new tasks, not exceptions.
Done when
An analyst pushes a template change; unsubmitted suppliers see it, submitted suppliers receive a reassigned task showing what changed.
What changes for you
Templates can change mid‑implementation. Suppliers may receive a second task; analysts no longer re‑issue by email.
6
Notes: The one slide that shows how, because it is the largest element and R03 and R11 depend on it. Keep it at the level of the picture: one task becomes several versioned tasks. Do not describe recipes. The bottom row is the same two columns the other groups have, so the slide still answers "done when" and "what changes."

## Slide 7: Some things appear, some change shape, and some stop being accepted.
WHAT WILL BE DIFFERENT
For suppliers
New
Rate calculator in the form, with an override reason
“Request an edit” after submission
“Flag for review” on a submission
A second task when a template changes
No longer accepted
Edits sent by email after submission
Placeholder values entered to pass validation
Reference data sent as an email attachment
For analysts
New
Configuration pages for the chosen steps (D3)
Batch‑add suppliers to a live implementation
Push a template version; see who gets reassigned
Edit history with attribution on every task
Different
Errors shown against the submitted rows
Seed mismatches stop the load instead of surfacing later
Edit requests and flags arrive as tasks, not emails
Need something else?
If your team needs something different from this list, the route is [change authority], not a message to the developer.
7
Notes: This is the expectation-setting slide: surface the surprises on purpose, especially the "no longer accepted" list. Pause here. If something on the right-hand column makes someone uncomfortable, better to hear it now. Close with the change route so the room knows where requests go.

## Slide 8: Four parts of SDC change. Most additions are a page or a step; the task record is the one thing rebuilt.
SYSTEM CHANGES
Supplier portal
Added
Reference‑data upload · R01
Rate calculator in the form · R02
“Request an edit” action · R03
“Flag for review” option · R04
Changed
Task list shows several tasks per supplier · R05
Analyst pages
Added
Configuration pages for chosen steps · R06
Batch‑add suppliers · R09
Push template version · R05
Seed validation report · R10
Changed
Error review in submitted shape · R08
Edit requests and flags arrive as tasks · R03 R04
Task record and data
Rebuilt
Task record carries version, owner and history · R05
Every process that reads “the task” reads “one of the tasks” · R05
Added
Reference‑data store with analyst access · R01
Edit history · R03
Configuration and validation
Added
Seed‑vs‑configuration check at load · R10
Rate rules as configuration · R02, pending
Retired
Workbook steps replaced by pages · R06, per D3
Unchanged
Validation rules themselves
Design is shown at the level of which parts change. How each part works is settled at the next gate and is not part of today’s approval.
8
Notes: This slide exists so the room can see that the functionality changes on the previous slide are grounded, and so nobody later says they did not know it would touch X. Keep it at the box level. If asked how a part works, answer in one sentence and offer the detail at the next gate; the footnote says so.

## Slide 9: Two elements are approved as scope today; their definitions come back at the next gate.
SUBJECT TO DEFINITION
R11 SOW support
SOW implementations send several documents over time, tied to milestones, instead of one roster upload. That needs phased templates and the task model on slide 6.
Approved today
The element, and its success test: one SOW implementation runs end to end in SDC.
Returns at the next gate
The SOW document set, which templates are phased, and the in/out list. SME time needed: SCM.
R02 Rate rules
The calculator is only as good as the rules behind it, and those live with the people who support the process today. Definition writes them down.
Approved today
The calculator (slide 4), and that the rules will be captured as configuration, not code.
Returns at the next gate
The rule set, whether it differs for MSP and SOW, and the override policy. SME time needed: the rate‑validation task owner.
Not a change request
Filling in these two definitions at the next gate is planned work. Altering an element approved today is a change, and goes through [change authority].
9
Notes: Be explicit about the shape of the approval: the element is in scope now, with a placeholder where its definition goes. The dark bar matters for the change authority: completing a planned placeholder is not a change request, so they are not asked to rule on things that were always scheduled. Name the SMEs so the room knows whose time the definition work needs.

## Slide 10: Three questions settle the shape of three elements; the rest are approved as written, modified, or deferred.
DECISIONS
D1 · R01 Master data
Is the file only stored, or does the system use it to populate configuration?
Stored only is small. Used downstream is not.
D2 · R03 In‑flight changes
Can a supplier request an edit at any state, or only before analyst approval?
“Any state” adds re‑approval handling.
D3 · R06 Configuration web app
Move all of configuration, or start with the steps that cause the most errors today?
Starting small lets it ship in phase 2.
Element | Approve as written | Modify | Defer
R02 Rate calculator · R04 Flag for review | ☐ | ☐ | ☐
R05 Template modifications (incl. task model) | ☐ | ☐ | ☐
R08 Error review · R09 Batch add · R10 Seed validation | ☐ | ☐ | ☐
R11 SOW support · R02 Rate rules — subject to definition | ☐ | ☐ | ☐
A deferred element is logged in the register’s change log on day one, with a reason, so the change authority starts with a complete queue.
10
Notes: Take D1–D3 first; each answer fixes an element's shape, and the register updates this week. Then walk the table row by row and record the outcome per row. Reviewers in a gated process need discrete items to record, not "the deck was approved." If an answer cannot be given today, record the owner and date; it becomes a gate condition on the next slide.

## Slide 11: Approve scope baseline v1.0, so definition work starts on [start date].
GATE DECISION
Go
Baseline v1.0 is frozen today; the register is versioned and the change log opens.
Go with conditions
Named items get an owner and a date; the baseline freezes when they close.
Hold
A decision in this room cannot be made today; we return on [date] with the same baseline.
Recycle
The baseline needs rework; we revise the register and resubmit.
Next gate · definition: R11 and R02 rule definitions, detailed design for the task record, refined estimates. Target [date].
Change authority of record: [name, role]. Baseline: requirements register v1.0, [date].
11
Notes: Restate the ask, offer the four gate outcomes, and close. Do not reopen the content. Whatever the outcome, say what they will see at the next gate and when. Record the change authority of record and the baseline version aloud so it is in the minutes.

## Slide 12: Supplier experience and SOW: what is in and what is out
APPENDIX A · BASELINE DETAIL
Element | In scope | Out of scope
R01 Master data upload | Secure upload via the portal; storage; analyst access | Validating the file; downstream use (pending D1)
R02 Rate calculator | Calculator in the supplier form; supplier‑facing messages; override handling; rules captured as configuration | Analyst review of calculated rates; validation of submitted rates; changing the rules
R03 In‑flight changes | Supplier edit request; edit history with attribution; analyst notification | Analyst edits on a supplier’s behalf; edits after close
R04 Flag for review | Submission‑level flag; immediate analyst task; bypass of rework loop | Field‑level flags; partial validation
R11 SOW support | Subject to definition; one SOW implementation end to end is the success test | Subject to definition
Full definitions, dependencies, and open questions are in the requirements register, baseline v1.0. Changes after approval are recorded in its change log.
A1
Notes: Reference only. Use when a stakeholder asks whether a specific thing is included.

## Slide 13: Analyst experience and platform: what is in and what is out
APPENDIX B · BASELINE DETAIL
Element | In scope | Out of scope
R05 Template modifications | Task record with versions, ownership and history (reused by R03, R11); push a new version; unsubmitted suppliers see it; submitted suppliers reassigned with deltas | Automatic migration of submitted data without supplier review
R06 Configuration web app | Web pages for the configuration steps chosen under D3, at parity with the workbook | Supplier form changes; steps not chosen for this phase
R07 Analyst training | Training before go‑live of each analyst‑facing element | Supplier training (covered by in‑portal messages)
R08 Error review in context | Failures shown in the submitted‑data shape | Changes to validation rules
R09 Batch add suppliers | Add several suppliers to a started implementation via the portal | Removing suppliers; reassigning suppliers
R10 Seed‑data validation | Validate seed data against configuration on load; report to the analyst | Automatic correction
A2
Notes: Reference only. R07's lines are a proposal; confirm the supplier-training exclusion with the training owner before the meeting.

## Slide 14: Four stages, each closed by a gate with written exit criteria; status is reported monthly between gates.
APPENDIX C · STAGE PLAN
Stage | Work | Closed by | Exit criteria
Scope · today | Requirements register, done‑when tests, functionality changes, system‑change map | Scope gate | Baseline v1.0 approved; D1–D3 answered; change authority named
Definition · month 1 | R11 and R02 rule definitions with SMEs; detailed design of the task record; quick wins R08–R10 built in parallel | Definition gate · [date] | R11 and R02 definitions approved into the baseline; task‑record design signed off; refined estimates
Build · months 2–3 | R05 foundation first, then R03 and R11 on it; R06 pages per D3; R01, R02 calculator, R04 | Build‑complete gate · [date] | Each element passes its done‑when test in the test environment; R07 training material ready
Validate and deploy · month 4 | Analyst UAT; one SOW implementation end to end; R07 training; staged go‑live | Go‑live gate · [date] | UAT signed off; done‑when tests pass in production for the first live implementation
Month boundaries are indicative; gate dates are set at the definition gate. Quick wins may release earlier than the build gate on the change authority’s approval.
A3
Notes: Reference. Decisions are made at the gates; the monthly reporting between them is status, not decision. If asked for dates, give the month and say the dates are fixed at the definition gate.

## Slide 15: Rough‑order‑of‑magnitude estimates; refined at the definition gate.
APPENDIX D · EFFORT BY ELEMENT
Element | What has to be built or changed | What makes it this size | ROM
R05 Template modifications · L | A task record that carries versions and ownership, so every process that reads “the supplier’s task” reads “one of the supplier’s tasks”; then notification, reassignment on the new version, and a view of what changed | Changes the estate rather than adding to it; [__] processes touched. R03 and R11 reuse this, which keeps them small | [__–__] wks
R06 Configuration web app · L | One analyst page per configuration step that leaves the workbook; the same checks the workbook applies today | The workbook’s rules exist only as spreadsheet logic and must be rewritten; range depends on D3 | [__–__] wks
R03 In‑flight changes · M | A supplier‑side “request an edit” action, an edit history, and an analyst notification | Rides on R05’s task model; grows if edits are allowed after approval (D2) | [__–__] wks
R02 Rate calculator · M | A calculator in the supplier form, and the rate rules captured as configuration | The build is small; capturing the rules is definition‑stage work and not sized until then | [__–__] wks
R11 SOW support · not sized | Subject to definition | Estimate is a deliverable of the definition gate | —
Quick wins · R04, R08, R09, R10: one page or one step each, no dependency on the above · [__] weeks total. R01 is one upload page unless D1 makes it more.
A4
Notes: Reference. Sizes justify the planning classes without explaining the build. These are rough-order-of-magnitude; the definition gate replaces them with ranges the room can hold you to. If someone asks for a date from this slide, point to appendix C.